## Sheet1
Already planned
| Date | MTP | Target | Channel | Aim | Actions
| 2021-11-23 | 47 | Phobos | LNO | Check pointing/detector row illumination and signal levels for first time | Define boresight offset N: will depend on results of first observation (deadline 6th Dec); start LNO patching (deadline: 14th Jan)
| 2021-12-05 | 48 | Phobos | UVIS |  | LNO boresight offset N deadline: 6th Dec
| 2021-12-22 | 48 | Phobos | LNO | Check pointing/detector row illumination
| 2021-12-29 | 49 | Deimos | LNO | Check pointing/detector row illumination w/ smaller target
| 2021-01-02 | 49 | Deimos | UVIS |  | Patching deadline: 14th Jan
| 2021-02-01 | 50 | Deimos | LNO | Check pointing/detector row illumination w/ smaller target
| 2021-02-02 | 50 | Deimos | UVIS |  | Patch applied: 19th Feb
| 2021-03-01 | 51 | Phobos | UVIS
| 2021-03-04 | 51 | Phobos | LNO | Check data w/ new LNO patches
To be planned
| 19th Mar+ | 52 | Phobos | LNO | LNO boresight with N arcminutes +Z offset
| 19th Mar+ | 52 | Phobos | LNO | LNO boresight with N arcminutes +Z offset | Decide on best LNO boresight (deadline 28 Mar!)
|  | 53 | Phobos | UVIS | UVIS with CaSSIS special pointing?
|  | 53 | Phobos | UVIS | UVIS with CaSSIS special pointing?
|  | 54 | Phobos | UVIS | UVIS with CaSSIS special pointing?
|  | 54 | Phobos | UVIS | UVIS with CaSSIS special pointing?
|  | 55 | Phobos | UVIS | UVIS with CaSSIS special pointing?
|  | 55 | Phobos | UVIS | UVIS with CaSSIS special pointing?
| 9th July+ | 56 | Phobos | LNO | Phobos observation campaign - many observations with best boresight and patched COP tables
For discussion:
Do we use MTP053 for more LNO offset boresights? Then shift everything after by 1 month
Or do we plan 4x LNO offset boresights in MTP052 and reduce the limbs by 2?
Do we reduce limbs in MTP053-55 to have a dedicated UVIS+CaSSIS campaign?
Can the 28th Mar deadline be extended by a few days? Otherwise LNO campaign shifts to August
Deadlines | Pointing | COP row | Execution start
MTP052 | 2021-12-06 | 2022-03-02 | 2022-03-19
MTP053 | 2022-01-03 | 2022-03-30 | 2022-04-16
MTP054 | 2022-01-31 | 2022-04-27 | 2022-05-14
MTP055 | 2022-02-28 | 2022-05-25 | 2022-06-11
MTP056 | 2022-03-28 | 2022-06-22 | 2022-07-09
These deadlines should be confirmed