## Sheet1
Already planned
Date | MTP | Target | Channel | Aim | Actions
2021-11-23 | 47 | Phobos | LNO | Check pointing/detector row illumination and signal levels for first time | Define boresight offset N: will depend on results of first observation (deadline 6th Dec); start LNO patching (deadline: 14th Jan)
2021-12-05 | 48 | Phobos | UVIS | CaSSIS ridealong | LNO boresight offset N deadline: 6th Dec, best case but still time until 14 January
2021-12-22 | 48 | Phobos | LNO | Check pointing/detector row illumination
2021-12-29 | 49 | Deimos | LNO | Check pointing/detector row illumination w/ smaller target
2021-01-02 | 49 | Deimos | UVIS |  | Patching deadline: 14th Jan (worst case, the sooner the better, also invite UVIS to submit their patch if they want to)
2021-02-01 | 50 | Deimos | LNO | Check pointing/detector row illumination w/ smaller target
2021-02-02 | 50 | Deimos | UVIS |  | Patch applied: 19th Feb
2021-03-01 | 51 | Phobos | UVIS
2021-03-04 | 51 | Phobos | LNO | Check data w/ new LNO patches
To be planned
19th Mar+ | 52 | Phobos | LNO | LNO boresight with N arcminutes +2 offset | Decide on best LNO boresight (deadline 28 Mar!)
19th Mar+ | 52 | Phobos | LNO | LNO boresight with N arcminutes -2 offset
19th Mar+ | 52 | Phobos | LNO | LNO boresight with N arcminutes +4 offset
19th Mar+ | 52 | Phobos | LNO | LNO boresight with N arcminutes -4 offset
| 53 | Phobos | UVIS | Short UVIS with CaSSIS special pointing | Decide UVIS duration, how many, if Phobos or Deimos (deadline 10 Jan)
| 53 | Phobos | UVIS | Short UVIS with CaSSIS special pointing | 5 per MTP x 3 MTPs
| 54 | Phobos | UVIS | Short UVIS with CaSSIS special pointing
| 54 | Phobos | UVIS | Short UVIS with CaSSIS special pointing
| 55 | Phobos / Deimos? | UVIS | Short UVIS with CaSSIS special pointing
| 55 | Phobos / Deimos? | UVIS | Short UVIS with CaSSIS special pointing
9th July+ | 56 | Phobos | LNO | Phobos observation campaign - many observations with best boresight and patched COP tables
|  | Plan for MTP053/054/055 |  | Plan for MTP056 | Plan for MTP057
|  | 13 pointings per MTP |  | 13 pointings per MTP | 13 pointings per MTP
|  | 6 Short UVIS phobos |  | 6 Long LNO Phobos | 4 Long LNO Phobos
|  | 3 Miniscans |  | 3 Miniscans | 3 Miniscans
|  | 0 Linescans |  | 0 Linescans | 2 Linescans
|  | 4 Limbs |  | 4 Limbs | 4 Limbs
Deadlines | Pointing | PTR freeze | COP row | Execution start
MTP052 | 2021-12-06 | 2022-01-14 | 2022-03-02 | 2022-03-19
MTP053 | 2022-01-10 | 2022-02-11 | 2022-03-30 | 2022-04-16
MTP054 | 2022-02-07 | 2022-03-11 | 2022-04-27 | 2022-05-14
MTP055 | 2022-03-07 | 2022-04-08 | 2022-05-25 | 2022-06-11
MTP056 | 2022-04-04 | 2022-05-06 | 2022-06-22 | 2022-07-09
These deadlines should be confirmed (confirmed by Bojan based on available inputs right now, same dates could maybe change due to Easter…)
Note that PTR freeze means pointing frozen between SOC-PI but in theory there’s still 1 week left to submit to FD (see MTP049 where our inputs with new SO LoS were inserted just days before submitting PTR files to FD)
This means that LNO boresight vectors could be provided anywhere between pointing and PTR freeze dates, of course rather closer to pointing date then to PTR freeze date
“Pointing” column means we need to provide the number of special pointings (e.g. 8 limbs, 4 mini-scans, 2 phobos) at that time which is kick-off – 2 weeks so that at kick-off time all special pointings + occultations are fixed.
At “pointing” column time we should specify what LoS to use but the LoS could still be tweaked before the PTR freeze deadline
|  |  | Person | Action | Deadline
|  |  | Bojan | Send MTP052 observation plan to SOC | 6th Dec
|  |  | Ian | Calculate LNO offset boresights | 14th Jan
|  |  | Bojan | Send UVIS+CaSSIS proposed plan to SOC (MTP053-055) | 10th Jan+
|  |  | Ian | Make SO and LNO patch | 14th Jan latest
|  |  | Jon | Make UVIS patch? | 14th Jan latest
|  |  | Ian | Choose best LNO boresight | 6th May?
|  |  | Jon | Choose best UVIS boresight? | 6th May?